## EXIS
SIMM 30C, Rev. 06/2014 | [5 empty] | EXISTING SYSTEM/BASELINE COST WORKSHEET
Agency/state entity: Dept. of Local Planning |  |  |  | All costs to be shown in whole (unrounded) dollars. | [8 empty] | Date Prepared: 5/6/2010
Project: Upgrade Database and Servers
| FY | 2009/10 | FY | 2010/11 | FY | 2011/12 | FY | 2012/13 | FY | 2013/14 | FY | 2014/15 |  | TOTAL
| PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts
Continuing Information
Technology Costs
Staff (salaries & benefits) | 1 | 50000 | 1 | 50000 | 1 | 50000 | 1 | 50000 | 0 | 0 | 0 | 0 | 4 | 200000
Hardware Lease/Maintenance |  | 15000 |  | 15000 |  | 15000 |  | 15000 |  | 0 |  | 0 |  | 60000
Software Maintenance/Licenses |  | 18000 |  | 18000 |  | 18000 |  | 18000 |  | 0 |  | 0 |  | 72000
Contract Services |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Data Center Services |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Agency Facilities |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Other |  | 7500 |  | 7500 |  | 7500 |  | 7500 |  | 0 |  | 0 |  | 30000
Total IT Costs | 1 | 90500 | 1 | 90500 | 1 | 90500 | 1 | 90500 | 0 | 0 | 0 | 0 | 4 | 362000
Continuing Program Costs:
Staff | 44 | 2083100 | 44 | 2083100 | 44 | 2083100 | 44 | 2083100 | 0 | 0 | 0 | 0 | 176 | 8332400
Other |  | 85000 |  | 85000 |  | 85000 |  | 85000 |  | 0 |  | 0 |  | 340000
Total Program Costs | 44 | 2168100 | 44 | 2168100 | 44 | 2168100 | 44 | 2168100 | 0 | 0 | 0 | 0 | 176 | 8672400
TOTAL EXISTING SYSTEM COSTS | 45 | 2258600 | 45 | 2258600 | 45 | 2258600 | 45 | 2258600 | 0 | 0 | 0 | 0 | 180 | 9034400

## ALT(P)
SIMM 30C, Rev. 06/2014 | PROPOSED ALTERNATIVE: |  |  | Upgrade Existing Database and Web Services
Date Prepared: 5/6/2010
Agency/state entity: Dept. of Local Planning |  |  | All Costs Should be shown in whole (unrounded) dollars.
Project: Upgrade Database and Servers
| FY | 2009/10 | FY | 2010/11 | FY | 2011/12 | FY | 2012/13 | FY | 2013/14 | FY | 2014/15 |  | TOTAL
| PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts
One-Time IT Project Costs
Staff (Salaries & Benefits) | 3 | 150000 | 3 | 150000 | 1 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 350000
Hardware Purchase |  | 75000 |  | 250698 |  | 0 |  | 0 |  | 0 |  | 0 |  | 325698
Software Purchase/License |  | 26950 |  | 75800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 102750
Telecommunications |  | 15000 |  | 7000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 22000
Contract Services
Software Customization |  | 25000 |  | 125000 |  | 20000 |  | 0 |  | 0 |  | 0 |  | 170000
Project Management |  | 19500 |  | 38750 |  | 5000 |  | 0 |  | 0 |  | 0 |  | 63250
Project Oversight |  | 15000 |  | 17890 |  | 2500 |  | 0 |  | 0 |  | 0 |  | 35390
IV&V Services |  | 30000 |  | 45000 |  | 6000 |  | 0 |  | 0 |  | 0 |  | 81000
Other Contract Services |  | 650 |  | 7800 |  | 50 |  | 0 |  | 0 |  | 0 |  | 8500
TOTAL Contract Services |  | 90150 |  | 234440 |  | 33550 |  | 0 |  | 0 |  | 0 |  | 358140
Data Center Services |  | 7900 |  | 1500 |  | 1000 |  | 0 |  | 0 |  | 0 |  | 10400
Agency Facilities |  | 2500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2500
Other |  | 12650 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 12650
Total One-time IT Costs | 3 | 380150 | 3 | 719438 | 1 | 84550 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1184138
Continuing IT Project Costs
Staff (Salaries & Benefits) | 0 | 0 | 0 | 0 | 0.5 | 25000 | 1 | 50000 | 0 | 0 | 0 | 0 | 1.5 | 75000
Hardware Lease/Maintenance |  | 500 |  | 3500 |  | 3500 |  | 3500 |  | 0 |  | 0 |  | 11000
Software Maintenance/Licenses |  | 2500 |  | 5000 |  | 7500 |  | 7500 |  | 0 |  | 0 |  | 22500
Telecommunications |  | 0 |  | 7500 |  | 15000 |  | 18000 |  | 0 |  | 0 |  | 40500
Contract Services |  | 15000 |  | 7500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 22500
Data Center Services |  | 2500 |  | 2500 |  | 2500 |  | 2500 |  | 0 |  | 0 |  | 10000
Agency Facilities |  | 0 |  | 1000 |  | 1000 |  | 1000 |  | 0 |  | 0 |  | 3000
Other |  | 5000 |  | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6000
Total Continuing IT Costs | 0 | 25500 | 0 | 28000 | 0.5 | 54500 | 1 | 82500 | 0 | 0 | 0 | 0 | 1.5 | 190500
Total Project Costs | 3 | 405650 | 3 | 747438 | 1.5 | 139050 | 1 | 82500 | 0 | 0 | 0 | 0 | 8.5 | 1374638
Continuing Existing Costs
Information Technology Staff | 1 | 50000 | 1 | 50000 | 0.5 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 125000
Other IT Costs |  | 40500 |  | 40500 |  | 20250 |  | 0 |  | 0 |  | 0 |  | 101250
Total Continuing Existing IT Costs | 1 | 90500 | 1 | 90500 | 0.5 | 45250 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 226250
Program Staff | 44 | 2083100 | 44 | 2083100 | 43 | 2036000 | 42 | 1988000 | 0 | 0 | 0 | 0 | 173 | 8190200
Other Program Costs |  | 85000 |  | 85000 |  | 65000 |  | 42500 |  | 0 |  | 0 |  | 277500
Total Continuing Existing Program Costs | 44 | 2168100 | 44 | 2168100 | 43 | 2101000 | 42 | 2030500 | 0 | 0 | 0 | 0 | 173 | 8467700
Total Continuing Existing Costs | 45 | 2258600 | 45 | 2258600 | 43.5 | 2146250 | 42 | 2030500 | 0 | 0 | 0 | 0 | 175.5 | 8693950
TOTAL ALTERNATIVE COSTS | 48 | 2664250 | 48 | 3006038 | 45 | 2285300 | 43 | 2113000 | 0 | 0 | 0 | 0 | 184 | 10068588
INCREASED REVENUES |  | 0 |  | 0 |  | 100000 |  | 150000 |  | 0 |  | 0 |  | 250000

## ALT (1)
SIMM 30C, Rev. 06/2014 | ALTERNATIVE #1: |  | New Generic Database, Web Enabled Applications
Date Prepared: 5/6/2010
Agency/state entity: Dept. of Local Planning |  |  | All Costs Should be shown in whole (unrounded) dollars.
Project: Upgrade Database and Servers
| FY | 2009/10 | FY | 2010/11 | FY | 2011/12 | FY | 2012/13 | FY | 2013/14 | FY | 2014/15 |  | TOTAL
| PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts
One-Time IT Project Costs
Staff (Salaries & Benefits) | 3 | 150000 | 3 | 150000 | 2 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 400000
Hardware Purchase |  | 495000 |  | 125000 |  | 95000 |  | 0 |  | 0 |  | 0 |  | 715000
Software Purchase/License |  | 255000 |  | 175000 |  | 55000 |  | 0 |  | 0 |  | 0 |  | 485000
Telecommunications |  | 75000 |  | 55000 |  | 25000 |  | 0 |  | 0 |  | 0 |  | 155000
Contract Services
Software Customization |  | 275000 |  | 195000 |  | 120000 |  | 0 |  | 0 |  | 0 |  | 590000
Project Management |  | 50000 |  | 45000 |  | 37500 |  | 0 |  | 0 |  | 0 |  | 132500
Project Oversight |  | 25000 |  | 18500 |  | 12500 |  | 0 |  | 0 |  | 0 |  | 56000
IV&V Services |  | 15000 |  | 12500 |  | 1000 |  | 0 |  | 0 |  | 0 |  | 28500
Other Contract Services |  | 650 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 650
TOTAL Contract Services |  | 365650 |  | 271000 |  | 171000 |  | 0 |  | 0 |  | 0 |  | 807650
Data Center Services |  | 7900 |  | 5500 |  | 2500 |  | 0 |  | 0 |  | 0 |  | 15900
Agency Facilities |  | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5000
Other |  | 12650 |  | 5425 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18075
Total One-time IT Costs | 3 | 1366200 | 3 | 786925 | 2 | 448500 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2601625
Continuing IT Project Costs
Staff (Salaries & Benefits) | 0 | 0 | 0 | 0 | 0.5 | 25000 | 1 | 50000 | 0 | 0 | 0 | 0 | 1.5 | 75000
Hardware Lease/Maintenance |  | 2500 |  | 3500 |  | 3500 |  | 3500 |  | 0 |  | 0 |  | 13000
Software Maintenance/Licenses |  | 2500 |  | 5000 |  | 8000 |  | 8000 |  | 0 |  | 0 |  | 23500
Telecommunications |  | 5500 |  | 16000 |  | 19000 |  | 22500 |  | 0 |  | 0 |  | 63000
Contract Services |  | 15000 |  | 7500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 22500
Data Center Services |  | 2500 |  | 2500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5000
Agency Facilities |  | 0 |  | 1000 |  | 1000 |  | 1000 |  | 0 |  | 0 |  | 3000
Other |  | 5000 |  | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6000
Total Continuing IT Costs | 0 | 33000 | 0 | 36500 | 0.5 | 56500 | 1 | 85000 | 0 | 0 | 0 | 0 | 1.5 | 211000
Total Project Costs | 3 | 1399200 | 3 | 823425 | 2.5 | 505000 | 1 | 85000 | 0 | 0 | 0 | 0 | 9.5 | 2812625
Continuing Existing Costs
Information Technology Staff | 1 | 50000 | 1 | 50000 | 0.5 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 125000
Other IT Costs |  | 40500 |  | 40500 |  | 20250 |  | 0 |  | 0 |  | 0 |  | 101250
Total Continuing Existing IT Costs | 1 | 90500 | 1 | 90500 | 0.5 | 45250 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 226250
Program Staff | 0 | 2083100 | 44 | 2083100 | 43 | 2036000 | 42 | 1988000 | 0 | 0 | 0 | 0 | 129 | 8190200
Other Program Costs |  | 85000 |  | 85000 |  | 65000 |  | 42500 |  | 0 |  | 0 |  | 277500
Total Continuing Existing Program Costs | 0 | 2168100 | 44 | 2168100 | 43 | 2101000 | 42 | 2030500 | 0 | 0 | 0 | 0 | 129 | 8467700
Total Continuing Existing Costs | 1 | 2258600 | 45 | 2258600 | 43.5 | 2146250 | 42 | 2030500 | 0 | 0 | 0 | 0 | 131.5 | 8693950
TOTAL ALTERNATIVE COSTS | 4 | 3657800 | 48 | 3082025 | 46 | 2651250 | 43 | 2115500 | 0 | 0 | 0 | 0 | 141 | 11506575
INCREASED REVENUES |  | 0 |  | 0 |  | 0 |  | 100000 |  | 0 |  | 0 |  | 100000

## ALT (2)
SIMM 30C, Rev. 06/2014 | ALTERNATIVE #2: |  | Custom Developed Databases, Web Enabled Applications
Date Prepared: 5/6/2010
Agency/state entity: Dept. of Local Planning |  |  | All Costs Should be shown in whole (unrounded) dollars.
Project: Upgrade Database and Servers
| FY | 2009/10 | FY | 2010/11 | FY | 2011/12 | FY | 2012/13 | FY | 2013/14 | FY | 2014/15 |  | TOTAL
| PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts
One-Time IT Project Costs
Staff (Salaries & Benefits) | 3 | 150000 | 3 | 150000 | 2 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 400000
Hardware Purchase |  | 495000 |  | 125000 |  | 95000 |  | 0 |  | 0 |  | 0 |  | 715000
Software Purchase/License |  | 255000 |  | 175000 |  | 55000 |  | 0 |  | 0 |  | 0 |  | 485000
Telecommunications |  | 75000 |  | 55000 |  | 25000 |  | 0 |  | 0 |  | 0 |  | 155000
Contract Services
Software Customization |  | 600000 |  | 300000 |  | 200000 |  | 0 |  | 0 |  | 0 |  | 1100000
Project Management |  | 50000 |  | 45000 |  | 37500 |  | 0 |  | 0 |  | 0 |  | 132500
Project Oversight |  | 25000 |  | 18500 |  | 12500 |  | 0 |  | 0 |  | 0 |  | 56000
IV&V Services |  | 15000 |  | 12500 |  | 1000 |  | 0 |  | 0 |  | 0 |  | 28500
Other Contract Services |  | 25000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25000
TOTAL Contract Services |  | 715000 |  | 376000 |  | 251000 |  | 0 |  | 0 |  | 0 |  | 1342000
Data Center Services |  | 7900 |  | 5500 |  | 2500 |  | 0 |  | 0 |  | 0 |  | 15900
Agency Facilities |  | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5000
Other |  | 12650 |  | 5425 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18075
Total One-time IT Costs | 3 | 1715550 | 3 | 891925 | 2 | 528500 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 3135975
Continuing IT Project Costs
Staff (Salaries & Benefits) | 0 | 0 | 0 | 0 | 0.5 | 25000 | 1 | 50000 | 0 | 0 | 0 | 0 | 1.5 | 75000
Hardware Lease/Maintenance |  | 2500 |  | 3500 |  | 3500 |  | 3500 |  | 0 |  | 0 |  | 13000
Software Maintenance/Licenses |  | 2500 |  | 5000 |  | 8000 |  | 8000 |  | 0 |  | 0 |  | 23500
Telecommunications |  | 5500 |  | 16000 |  | 19000 |  | 22500 |  | 0 |  | 0 |  | 63000
Contract Services |  | 15000 |  | 7500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 22500
Data Center Services |  | 2500 |  | 2500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5000
Agency Facilities |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Other |  | 5000 |  | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6000
Total Continuing IT Costs | 0 | 33000 | 0 | 35500 | 0.5 | 55500 | 1 | 84000 | 0 | 0 | 0 | 0 | 1.5 | 208000
Total Project Costs | 3 | 1748550 | 3 | 927425 | 2.5 | 584000 | 1 | 84000 | 0 | 0 | 0 | 0 | 9.5 | 3343975
Continuing Existing Costs
Information Technology Staff | 1 | 50000 | 1 | 50000 | 0.5 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 125000
Other IT Costs |  | 40500 |  | 40500 |  | 20250 |  | 0 |  | 0 |  | 0 |  | 101250
Total Continuing Existing IT Costs | 1 | 90500 | 1 | 90500 | 0.5 | 45250 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 226250
Program Staff | 44 | 2083100 | 44 | 2083100 | 43 | 2036000 | 42 | 1988000 | 0 | 0 | 0 | 0 | 173 | 8190200
Other Program Costs |  | 85000 |  | 85000 |  | 65000 |  | 42500 |  | 0 |  | 0 |  | 277500
Total Continuing Existing Program Costs | 44 | 2168100 | 44 | 2168100 | 43 | 2101000 | 42 | 2030500 | 0 | 0 | 0 | 0 | 173 | 8467700
Total Continuing Existing Costs | 45 | 2258600 | 45 | 2258600 | 43.5 | 2146250 | 42 | 2030500 | 0 | 0 | 0 | 0 | 175.5 | 8693950
TOTAL ALTERNATIVE COSTS | 48 | 4007150 | 48 | 3186025 | 46 | 2730250 | 43 | 2114500 | 0 | 0 | 0 | 0 | 185 | 12037925
INCREASED REVENUES |  | 0 |  | 0 |  | 100000 |  | 150000 |  | 0 |  | 0 |  | 250000

## SUM3
SIMM 30C, Rev. 06/2014 | [5 empty] | ECONOMIC ANALYSIS SUMMARY | [6 empty] | Date Prepared: 5/6/2010
Agency/state entity: Dept. of Local Planning |  |  |  | All costs to be shown in whole (unrounded) dollars.
Project: Upgrade Database and Servers
| FY | 2009/10 | FY | 2010/11 | FY | 2011/12 | FY | 2012/13 | FY | 2013/14 | FY | 2014/15 |  | TOTAL
| PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts
EXISTING SYSTEM
Total IT Costs | 1 | 90500 | 1 | 90500 | 1 | 90500 | 1 | 90500 | 0 | 0 | 0 | 0 | 4 | 362000
Total Program Costs | 44 | 2168100 | 44 | 2168100 | 44 | 2168100 | 44 | 2168100 | 0 | 0 | 0 | 0 | 176 | 8672400
Total Existing System Costs | 45 | 2258600 | 45 | 2258600 | 45 | 2258600 | 45 | 2258600 | 0 | 0 | 0 | 0 | 180 | 9034400
PROPOSED ALTERNATIVE | Upgrade Existing Database and Web Services
Total Project Costs | 3 | 405650 | 3 | 747438 | 1.5 | 139050 | 1 | 82500 | 0 | 0 | 0 | 0 | 8.5 | 1374638
Total Cont. Exist. Costs | 45 | 2258600 | 45 | 2258600 | 43.5 | 2146250 | 42 | 2030500 | 0 | 0 | 0 | 0 | 175.5 | 8693950
Total Alternative Costs | 48 | 2664250 | 48 | 3006038 | 45 | 2285300 | 43 | 2113000 | 0 | 0 | 0 | 0 | 184 | 10068588
COST SAVINGS/AVOIDANCES | -3 | -405650 | -3 | -747438 | 0 | -26700 | 2 | 145600 | 0 | 0 | 0 | 0 | -4 | -1034188
Increased Revenues |  | 0 |  | 0 |  | 100000 |  | 150000 |  | 0 |  | 0 |  | 250000
Net (Cost) or Benefit | -3 | -405650 | -3 | -747438 | 0 | 73300 | 2 | 295600 | 0 | 0 | 0 | 0 | -4 | -784188
Cum. Net (Cost) or Benefit | -3 | -405650 | -6 | -1153088 | -6 | -1079788 | -4 | -784188 | -4 | -784188 | -4 | -784188
ALTERNATIVE #1 | New Generic Database, Web Enabled Applications
Total Project Costs | 3 | 1399200 | 3 | 823425 | 2.5 | 505000 | 1 | 85000 | 0 | 0 | 0 | 0 | 9.5 | 2812625
Total Cont. Exist. Costs | 1 | 2258600 | 45 | 2258600 | 43.5 | 2146250 | 42 | 2030500 | 0 | 0 | 0 | 0 | 131.5 | 8693950
Total Alternative Costs | 4 | 3657800 | 48 | 3082025 | 46 | 2651250 | 43 | 2115500 | 0 | 0 | 0 | 0 | 141 | 11506575
COST SAVINGS/AVOIDANCES | 41 | -1399200 | -3 | -823425 | -1 | -392650 | 2 | 143100 | 0 | 0 | 0 | 0 | 39 | -2472175
Increased Revenues |  | 0 |  | 0 |  | 0 |  | 100000 |  | 0 |  | 0 |  | 100000
Net (Cost) or Benefit | 41 | -1399200 | -3 | -823425 | -1 | -392650 | 2 | 243100 | 0 | 0 | 0 | 0 | 39 | -2372175
Cum. Net (Cost) or Benefit | 41 | -1399200 | 38 | -2222625 | 37 | -2615275 | 39 | -2372175 | 39 | -2372175 | 39 | -2372175
ALTERNATIVE #2 | Custom Developed Databases, Web Enabled Applications
Total Project Costs | 3 | 1748550 | 3 | 927425 | 2.5 | 584000 | 1 | 84000 | 0 | 0 | 0 | 0 | 9.5 | 3343975
Total Cont. Exist. Costs | 45 | 2258600 | 45 | 2258600 | 43.5 | 2146250 | 42 | 2030500 | 0 | 0 | 0 | 0 | 175.5 | 8693950
Total Alternative Costs | 48 | 4007150 | 48 | 3186025 | 46 | 2730250 | 43 | 2114500 | 0 | 0 | 0 | 0 | 185 | 12037925
COST SAVINGS/AVOIDANCES | -3 | -1748550 | -3 | -927425 | -1 | -471650 | 2 | 144100 | 0 | 0 | 0 | 0 | -5 | -3003525
Increased Revenues |  | 0 |  | 0 |  | 100000 |  | 150000 |  | 0 |  | 0 |  | 250000
Net (Cost) or Benefit | -3 | -1748550 | -3 | -927425 | -1 | -371650 | 2 | 294100 | 0 | 0 | 0 | 0 | -5 | -2753525
Cum. Net (Cost) or Benefit | -3 | -1748550 | -6 | -2675975 | -7 | -3047625 | -5 | -2753525 | -5 | -2753525 | -5 | -2753525

## FUND
SIMM 30C, Rev. 06/2014 | PROJECT FUNDING PLAN
Agency/state entity: Dept. of Local Planning |  | All Costs to be in whole (unrounded) dollars | [10 empty] | Date Prepared: 5/6/2010
Project: Upgrade Database and Servers
| FY | 2009/10 | FY | 2010/11 | FY | 2011/12 | FY | 2012/13 | FY | 2013/14 | FY | 2014/15 | TOTALS
| PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts
TOTAL PROJECT COSTS | 3 | 405650 | 3 | 747438 | 1.5 | 139050 | 1 | 82500 | 0 | 0 | 0 | 0 | 8.5 | 1374638
RESOURCES TO BE REDIRECTED
Staff | 0 | 0 | 0 | 0 | 0.5 | 25000 | 1 | 50000 |  | 0 | 0 | 0 | 1.5 | 75000
Funds:
Existing System |  | 0 |  | 0 |  | 20250 |  | 32500 |  | 0 |  | 0 |  | 52750
Other Fund Sources |  | 18500 |  | 18500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 37000
TOTAL REDIRECTED RESOURCES | 0 | 18500 | 0 | 18500 | 0.5 | 45250 | 1 | 82500 | 0 | 0 | 0 | 0 | 1.5 | 164750
ADDITIONAL PROJECT FUNDING NEEDED
One-Time Project Costs | 3 | 380150 | 0 | 719438 | 1 | 84550 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1184138
Continuing Project Costs | 0 | 7000 | 0 | 9500 | 0 | 9250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25750
TOTAL ADDITIONAL PROJECT FUNDS NEEDED BY FISCAL YEAR | 3 | 387150 | 0 | 728938 | 1 | 93800 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1209888
TOTAL PROJECT FUNDING | 3 | 405650 | 0 | 747438 | 1.5 | 139050 | 1 | 82500 | 0 | 0 | 0 | 0 | 5.5 | 1374638
Difference: Funding - Costs | 0 | 0 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 0
Total Estimated Cost Savings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FUNDING SOURCE*
General Fund | 35% | 141977.5 | 35% | 261603.3 | 50% | 69525 | 100% | 82500 | 0% | 0 | 0% | 0 | 40.42% | 555605.8
Federal Fund | 65% | 263672.5 | 65% | 485834.7 | 50% | 69525 | 0% | 0 | 0% | 0 | 0% | 0 | 59.58% | 819032.2
Special Fund | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
Reimbursement | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
TOTAL FUNDING | 100% | 405650 | 100% | 747438 | 100% | 139050 | 100% | 82500 | 0% | 0 | 0% | 0 | 100% | 1374638
*Type: If applicable, for each funding source, beginning on row 29, describe what type of funding is included, such as local assistance or grant funding, the date the funding is to become available, and the duration of the funding.
Federal Funding from grant xxx for 3 years, beginning July 1, 2010.
SIMM 30C, Rev. 06/2014 | ADJUSTMENTS, SAVINGS AND REVENUES WORKSHEET
Agency/state entity: Dept. of Local Planning | [12 empty] | Date Prepared: 5/6/2010
Project: Upgrade Database and Servers
| FY | 2009/10 | FY | 2010/11 | FY | 2011/12 | FY | 2012/13 | FY | 2013/14 | FY | 2014/15 | Net Adjustments
Annual Project Adjustments | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts | PYs | Amts
One-time Costs
Previous Year's Baseline | 0 | 0 | 3 | 380150 | 0 | 719438 | 1 | 84550 | 0 | 0 | 0 | 0
(A) Annual Augmentation /(Reduction) | 3 | 380150 | -3 | 339288 | 1 | -634888 | -1 | -84550 | 0 | 0 | 0 | 0
(B) Total One-Time Budget Actions | 3 | 380150 | 0 | 719438 | 1 | 84550 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1184138
Continuing Costs
Previous Year's Baseline | 0 | 0 | 0 | 7000 | 0 | 9500 | 0 | 9250 | 0 | 0 | 0 | 0
(C) Annual Augmentation /(Reduction) | 0 | 7000 | 0 | 2500 | 0 | -250 | 0 | -9250 | 0 | 0 | 0 | 0
(D) Total Continuing Budget Actions | 0 | 7000 | 0 | 9500 | 0 | 9250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25750
Total Annual Project Budget Augmentation /(Reduction) [A + C] | 3 | 387150 | -3 | 341788 | 1 | -635138 | -1 | -93800 | 0 | 0 | 0 | 0
[A, C] Excludes Redirected Resources
|  | Total Additional Project Funds Needed [B + D] | [10 empty] | 4 | 1209888
Annual Savings/Revenue Adjustments
Cost Savings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Increased Program Revenues |  | 0 |  | 0 |  | 100000 |  | 150000 |  | 0 |  | 0