## Complexity Assessment
Project Name:
Complexity Assessment
Technology Agency Project #:
Department:
Revision Date:
Business Complexity
Instructions: On a scale of .5 - low to 4-high (0 = N/A), rate each applicable attribute and compute the Business Complexity by dividing the total by the number of items rated above zero. [Notes: Business and technical complexity will be computed automatically in this worksheet, using the ratings you enter. Move your pointer over each attribute cell, marked with a red triangle, to see a definition of the attribute.]
|  | Low Complexity |  |  | Business Attribute |  |  |  | High Complexity |  | Rating
0 1 2 3 4
|  | Static |  |  | Business rules |  |  |  | Changing
|  | Static |  |  | Current Business Systems |  |  |  | Changing
|  | Known and Followed |  |  | Decision Making Process |  |  |  | Not Known
|  | Low |  |  | Financial Risk to State |  |  |  | High
|  | Local |  |  | Geography |  |  |  | State Wide
|  | Clear and Stable |  |  | High Level Requirements |  |  |  | Vague
|  | Few & Routine |  |  | Interaction with Other Departments and Entities |  |  |  | Many and New
|  | None |  |  | Impact to Business Process |  |  |  | High
|  | Few & Straight Forward |  |  | Issues |  |  |  | Multiple & Contentious
|  | High |  |  | Level of Authority |  |  |  | Low
|  | Clear |  |  | Objectives |  |  |  | Vague
|  | Established |  |  | Policies |  |  |  | Non-existent
|  | Minimal |  |  | Politics |  |  |  | High
|  | Familiar |  |  | Target Users |  |  |  | Unfamiliar
|  | Experienced |  |  | Project Manager's Experience |  |  |  | Inexperienced
|  | Experienced |  |  | Team |  |  |  | Inexperienced
|  | Loose |  |  | Time Scale |  |  |  | Tight
|  | Low |  |  | Visibility |  |  |  | High
[10 empty] | Total: | 0
[10 empty] | Complexity: | 0
Technical Complexity
Instructions: On a scale of 0-low to 4-high, rate each applicable attribute and compute the Technical Complexity by dividing the total by the number of items rated above zero. Use the definitions in the student notebook for clarity.
|  | Low Complexity |  |  | Technical Attribute |  |  |  | High Complexity |  | Rating
0 1 2 3 4
|  | Local |  |  | Communications |  |  |  | State wide
|  | Established |  |  | Delivery Mechanism |  |  |  | New
|  | Local |  |  | Geography |  |  |  | State wide
|  | Proven |  |  | Hardware |  |  |  | New
|  | Stand-alone |  |  | Level Of Integration |  |  |  | Tightly Integrated
|  | Proven/Stable |  |  | Networks (L/W) |  |  |  | New
|  | In place |  |  | New Technology Architecture |  |  |  | Not in place
|  | 9-5, Mon-Fri |  |  | Operations |  |  |  | 24-hour, 7-day
|  | Expert |  |  | PM Technical Experience |  |  |  | Novice
|  | Established and in use |  |  | Scope Management Process |  |  |  | None
|  | Light |  |  | Security |  |  |  | Tight
|  | Proven |  |  | Software |  |  |  | New
|  | Established and In Use |  |  | Standards And Methods |  |  |  | None
|  | Experienced |  |  | Team |  |  |  | Inexperienced
|  | High |  |  | Tolerance To Fault |  |  |  | Low
|  | Low |  |  | Transaction Volume |  |  |  | High
[10 empty] | Total: | 0 | 0
[10 empty] | Complexity: | 0
Complexity Diagram
Instructions: Plot your project in the appropriate complexity zone. [Note: Your project will be plotted automatically in this worksheet, using the values computed in the previous tables.]
|  |  | Scores | Business Complexity |  |  | 0
|  |  |  | Technical Complexity |  |  | 0
Suggested Project Manager Skill Set Guidelines
| Complexity |  |  |  | Duration |  |  |  | Budget |  |  | Resources |  | Complexity |  | Duration |  | Budget |  | Resources |  | Score | Level | Guidelines
|  | Zone 1 |  |  |  | < 6 months |  |  |  | <$500K |  |  | < 5 | FALSE | 25 | TRUE | 20 | TRUE | 20 | TRUE | 20 | 33 - 40 | Novice | Experience: Minimum 1 year working as a key team member on an IT project. Technical experience commensurate with the proposed technology.
|  | Zone II, Medium Zone III, Medium |  |  |  | < 1 year |  |  |  | <$1M |  |  | <10 | TRUE | 50 | FALSE | 40 | FALSE | 40 | FALSE | 40 |  |  | Professional Knowledge: Understands the CA-PMM and department’s methodology.
|  | Zone II, High Zone III, High |  |  |  | >1 year; < 3 years |  |  |  | >$1M; <$5M |  |  | 11 – 20 | FALSE | 75 | FALSE | 60 | FALSE | 60 | FALSE | 60 | 41 - 50 | 1 | Experience: Minimum 3 years working as a key team member on an IT project or as a Project Manager on other small IT projects. Technical experience commensurate with the proposed technology.
|  | Zone IV |  |  |  | >3 years; <10 years |  |  |  | >$5M; <$100M |  |  | 21 – 40 | FALSE | 100 | FALSE | 80 | FALSE | 80 | FALSE | 80 |  |  | Professional Knowledge: Understands the CA-PMM and department’s methodology.
[6 empty] | >10 years |  |  |  | >$100M |  |  | 40+ |  |  | FALSE | 100 | FALSE | 100 | FALSE | 100 | 51 - 75 | 2 | Experience: 3 – 5 years as a key team member on a medium or large IT project or as a Project Manager on small or medium IT project. Technical experience commensurate with the proposed technology.
| 50 | 35% |  |  | 20 | 15% |  |  | 20 | 35% |  | 20 | 15%
30.5
| PM Level: |  |  |  | Novice | Experience: Minimum 1 year working as a key team member on an IT project. Technical experience commensurate with the proposed technology. | [17 empty] | Professional Knowledge: Strong working knowledge of the CA-PMM, department’s methodology, Software Development Life Cycle. Familiar with CA Budgeting, Procurement and Contracting processes.
[6 empty] | Professional Knowledge: Understands the CA-PMM and department’s methodology. | [15 empty] | 76 - 90 | 3 | Experience: 3-5 years working as Project Manager on medium or other large IT projects. Technical experience commensurate with the proposed technology.
For Oversight Purposes: | [23 empty] | Professional Knowledge: Strong working knowledge of the CA-PMM, department’s methodology, Software Development Life Cycle. Familiar with CA Budgeting, Procurement and Contracting processes.
Zone I = Low Criticality/Risk
Zones II and III = Medium Criticality/Risk | [5 empty] | Assess the complexity of the project periodically: every two - three months and/or at the conclusion of each phase | [15 empty] | 91+ | 4 | Experience: 5+ years working as Project Manager or Project Director on large IT projects . Technical experience commensurate with the proposed technology.
Zone IV = High Criticality/Risk | [23 empty] | Professional Knowledge: Strong working knowledge of the CA-PMM; CA Budgeting, Procurement and Contracting processes; department’s methodology; and Software Development Life Cycle.
I
III
Low Complexity
High
Complexity
Medium
Complexity
(Technical)
Medium
Complexity
(Business)
Note on G15: The degree to which business rules governing the industry either are in place and constant, or are growing and changing with the demands of the business.
Note on G16: The number and complexity of current business systems the project must interact with (e.g. approval processes, purchasing systems, etc.)
Note on G17: A description of the authorities and individuals involved in making the decisions required by the project.
Note on G18: The size of the money that is at stake for the State.
Note on G19: The areas in which the project must be managed and implemented.
Note on G20: The clarity and completeness of the functional requirements for the project.
Note on G21: The degree to which the team must interact with and rely on other departments to complete the work involved in the project.
Note on G22: The degree to which existing business processes will be impacted by the project.
Note on G23: The number and type of unanswered questions or differences of opinion that exist about the project.
Note on G24: The authority that the project team has to make decisions regarding the project.
Note on G25: The extent to which the end goal of the project is specific, measurable, achievable, relevant to overall strategy, and time-bound.
Note on G26: Organizational rules or regulations that may impact the project.
Note on G27: The degree of competition between competing interest groups or individuals for power and/or leadership.
Note on G28: The individuals who are intended to use the product of the project.
Note on G30: The average level of experience possessed by the team in the business functions required by the project.
Note on G31: The tightness of the development schedule for the project.
Note on G32: The degree that the outcome of the project is visible to upper management, stockholders, and the general public.
Note on L35: Summation of business complexity rankings.
Note on L36: The average of score of the items rated above zero.
Note on G44: The area(s) to which communications to the project will be needed.
Note on G45: The method by which the products of the project will be delivered to the client.
Note on G46: The area(s) where the project will be implemented.
Note on G47: Machinery and equipment: CPU, disks, tapes, modem, cables, printers, monitors, etc.
Note on G48: The degree to which the project combines the activities of multiple applications or systems.
Note on G49: LAN: A communications network that serves users within a confined geographical area. It is made up of servers, workstations, a network operating system and a communications link. WAN: A communications network that serves a wide geographical area such as a state or a country. A WAN requires the network facilities of common carriers.
Note on G50: The design of a computer system setting the standard for all devices that connect to it and all the software that runs on it.
Note on G51: The hours that the product (or the project) will be in use.
Note on G52: The level of project specific technical knowledge and experience possessed by the project manager.
Note on G53: The process by which change to scope is evaluated and then either dropped or integrated into the project.
Note on G54: The degree to which the project needs protection from theft, copying, or corruption.
Note on G55: Instructions for the computer: system software is made up of control programs, and application software is any program that processes data.
Note on G56: The specifications and practices for either software or hardware that are widely in use that will guide us through the development of the project.
Note on G57: The technical experience level of the team.
Note on G58: The degree to which defects can be tolerated.
Note on G59: Number of requests, activities, orders, etc.
Note on L63: Summation of technical complexity rankings.
Note on L64: The average of score of the items rated above zero.