## Instructions
INSTRUCTIONS
Complexity Assessment Evaluation
OVERVIEW: | This self-assessment provides insight into potential vulnerabilities that may influence your project. When the project team is aware of possible weaknesses upfront, it enables the resources to focus on vital components, mitigate risks, and contribute to organizational success and resilience. This assessment scores your answers with a rating of 1-5. The higher your score, the higher the complexity. A high score should not necessarily be a barrier to moving forward. Instead, include mitigation strategies in your planning for the areas where additional organizational and/or technical readiness work may be appropriate.
PURPOSE: | To guide future planning of the project and to identify, evaluate, and develop proactive actions to mitigate any discovered risks.
INSTRUCTIONS: | Following the Ideation Phase and before completing Chapter 1, read and answer each question in all three (3) knowledge areas. Enter the value for the finding (1-5), with the highest being the most significant. The project team is encouraged to complete the assessment together. Once completed, review the 'Bar' in the Summary Score tab to see your project's complexity level. After you complete each chapter of the Workbook, you will need to revisit the Complexity Assessment. If any of your question scores have changed due to project circumstances, please indicate this by answering yes in the top section of the Questions tab. Additionally, provide a reason for any changes in your question scores for better clarity.
Project Team Members Completing Assessment (List Names and Roles)
| NAME: | Example Roles:
Project Manager
Technical Lead
Product Owner
Risk Manager
Enterprise Architect
Developer
Business Analyst

## Questions
Project Complexity Assessment
Date: XX/XX/XXXX |  | State Entity: | What Chapter/Phase are you completing?
Project #: |  |  | Have any of your answers changed from previous submissions? (if no, submit a blank assessment)
Project Name: |  |  | If your score on any question has changed, enter the reason:
Knowledge Area | Number | Question | Complexity Level | The higher your score, the more complex your project will be. (If more than 1 answer applies, select the highest complexity level)
|  | Business | Enter 1.00-5.00 | Level = 1 | Level = 2 | Level = 3 | Level = 4 | Level = 5
Business | 1.1 | What is the estimated project cost? |  | 10,000,000 or under | $10,000,001 - $25,000,000 | $25,000,001 - $50,000,000 | $50,000,001 - $100,000,000 | $100,000,001 or above
| 1.2 | What is the potential financial risk the project imposes on the State if scope, schedule, and cost are not met? |  | Reduced Cash Flow (Operational) | Contractual/Legal Penalties (Moderate) | Inflation Risk (High) | Loss of Funding or Grants (Very High) | Significant Budget Overruns (Extremely High)
| 1.3 | What is the anticipated funding source for the project? |  | State Grant | State General Funds | Budget Change Proposal funds (BCP) | Federal Funds | Undetermined
| 1.4 | What is the primary impact on the State if this project is not completed? |  | No Impact | Audit impact | Legislative impact | Financial impact | Legal impact
| 1.5 | What is the degree to which the project's outcome is visible to executives, external stakeholders, legislators, the Governor's Office, or the general public? |  | Lowest Visibility Restricted to internal project team | Low Visibility On-demand Executive Summary | Medium Visibility Dashboards & regular status reporting | High Visibility Public-facing dashboard & legislative updates | Highest Visibility Full transparency & 3rd-party audit access
| 1.6 | Specify the total number of users of the application. |  | 100 or less | 1,000 or less | 5,000 or less | 50,000 or less | 50,000 or more
| 1.7 | What is the degree to which organizational rules or regulations exist and may impact the project? |  | Negligible Impact Rules exist but are guidelines | Low Impact Adherence to rules is expected but flexible | Moderate Impact Changes to the project require approval from a PMO or functional manager | High Impact Rigid, formalized rules for management control | Critical Impact All activities are restricted by detailed, inflexible regulations
| 1.8 | To what extent are documented business rules stable versus changing over a defined period (e.g., past 12 months)? |  | Fully documented, governed, and rarely changed (<5% updated annually) | Most rules documented; limited change (<20% updated annually) | Some rules documented; moderate change (20-50% updated annually) | Rules are mostly ad hoc and frequently changing (>50% updated annually) | No documented rules
| 1.9 | Select the number of Programs where business processes are being automated. |  | 1 | 2 | 3 | 4 | 5 or greater
| 1.1 | What is the degree to which existing business processes will be impacted by the project? |  | Negligible Impact (<1% change) | Minor Impact (1-10% change) | Moderate Impact (11-30% change) | Major impact (31-60%) | Transformational Impact (>60% change)
| 1.11 | At what level have requirements been documented, validated, and traced? (Refer to the PDL Glossary for the definitions of requirements categories.) https://projectresources.cdt.ca.gov/project-delivery-lifecycle/ |  | Business/ User/ Functional/ Non-Functional Transitional | Business/ User/ Functional/ Non-Functional | Business/ User/ Functional level | Business level & User level | Business level only
| 1.12 | What is the total number of agreed-upon functional requirements? |  | 100-280 | 281-460 | 461-640 | 641-820 | 821-1,000+
| 1.13 | Of the total number of agreed-upon functional requirements, what percentage are mandatory versus optional? |  | Low Mandatory 0% - 20% | Minority Essential 21% - 40% | Balanced Scope 41% - 60% | High Criticality 61% - 85% | Strict Compliance 86% - 100%
| 1.14 | What is the number of internal and external interfaces the project must interact with and rely upon to complete business process activities? |  | 1 | 2 | 3 | 4 | 5 or greater
| 1.15 | Select the level of authority given to the project team to make project business decisions. |  | Act Independently 100% authority given to the project team to achieve final outcomes | Decide & Inform < 10% of team decisions are reviewed or corrected by leadership | Research & Recommend >75% of team decisions meet approval of leadership | Research & Report 90-100% business-impacting decision require sign-off | Direct Supervision 100% tasks require sign-off outside the project team
| 1.16 | What is the degree to which unanswered questions or differences of opinion exist about the project requirements? |  | Negligible Uncertainty (0-5% scope volatility) | Low Uncertainty (10-20% requirements variance) | Moderate Uncertainty (25%-40% scope changes) | High Uncertainty (>50% volatility - requirements in flux) | Extreme Uncertainty No defined baseline, severe stakeholder conflict
| 1.17 | What is the degree of influence on the project leadership asserted from external stakeholders, legislators, the Governor's Office, or the general public? |  | Minimal influence Monitor only | Low Influence Regular notification & information | Moderate Influence Active consultation & input | High Influence Co-creation & shared decision-making | Determinative Influence Directs & mandates
|  | AVERAGE TOTAL | 0 | The higher your score, the more complex your project will be.
|  | Project Management | Enter 1.00-5.00 | Level = 1 | Level = 2 | Level = 3 | Level = 4 | Level = 5
Project Management / Governance | 2.1 | Does the organization have enterprise-wide IT project portfolio management processes with a dedicated IT Project Management Office (PMO)? |  | Organizational strategic goals are incorporated, weighted, and prioritized in an IT Project Portfolio managed by the Project Management Office (PMO) | IT project portfolio management processes are documented and followed by the Project Management Office (PMO) | IT projects are managed either by the business or the IT teams with no governance process to direct organizational strategic goals and prioritization | Portfolios are managed separately by multiple business programs | No established enterprise-wide IT project portfolio in place
| 2.2 | Select the structure that best describes the IT Project Management Office (PMO) within your organization. |  | The IT PMO plays a directive role, utilizing standardized processes that are followed | The IT PMO plays a directive role | The IT PMO plays a controlling role | The IT PMO plays a supportive role to project teams | No IT PMO in the organization
| 2.3 | To what extent do external stakeholders (suppliers, clients, regulatory bodies) influence the decision-making process, and how aligned is the governance structure (Steering Committee, Change Board) to manage these, along with internal stakeholders? |  | Governance structure is internal only, well-documented, and fully empowered | Clear governance with designated liaisons to manage minor, non-critical input from a small number of external stakeholders | Formal governance includes key external stakeholders; decision-making is structured but requires negotiation | Numerous high-power external stakeholders with competing interests require frequent, complex, and high-level steering committee negotiations to reach consensus | Multiple conflicting external entities have authority to halt the project. Governance is highly fragmented, requiring specialized, often political, navigation and continuous renegotiation
| 2.4 | Are there well-documented, repeatable project escalation procedures in place? |  | Project escalation is documented, followed, and flows to the highest level | Project escalation is documented | Project escalation occurs within business programs | Project escalation occurs ad hoc without documented processes | No documented project escalation procedures
| 2.5 | How many dedicated state resources are estimated to complete this project? |  | 5 or less | 6-10 | 11-15 | 26-50 | 50+
| 2.6 | What is the project sponsor's experience leading a project in similar solution implementations? |  | 4+ prior implementations | 3 prior implementations | 2 prior implementations | 1 prior implementation | 0 prior implementations
| 2.7 | What is the state project manager's experience leading a project team in similar solution implementations? |  | 4+ prior implementations | 3 prior implementations | 2 prior implementations | 1 prior implementation | 0 prior implementations
| 2.8 | What is the state project team's experience planning and executing in similar solution implementations (product owner, lead EA, lead ISO, lead procurement analyst, lead budget officer, developer(s), infrastructure)? |  | 4+ prior implementations | 3 prior implementations | 2 prior implementations | 1 prior implementation | 0 prior implementations
| 2.9 | Have staff resources been identified to manage the project contract and vendor deliverables? |  | Dedicated and trained contract manager has been assigned to manage contract/vendor deliverables | Project resource(s) have been assigned to manage contract/vendor deliverables | Project manager will manage the contract and deliverables | Staff not associated with the project have been assigned to manage contract/vendor deliverables | No staff assigned
| 2.10 | Are there constraints on the project schedule? |  | The schedule is fluid | Scheduled start and finish dates are documented but flexible | The schedule has a fixed start date | The schedule has a fixed finish date | The schedule has fixed start and finish dates with mandatory milestones
| 2.11 | What is the expected project execution duration? |  | <12 mos. | 12-18 mos. | 18-24 mos. | 24-36 mos. | 36 mos.+
|  | AVERAGE TOTAL | 0 | The higher your score, the more complex your project will be.
|  | Technical | Enter 1.00-5.00 | No = 1 |  |  |  | Yes = 5
Environment and Technology (The first 4 questions are focused on legacy systems) | 3.1 | Does your anticipated solution include a replacement for legacy systems? If your answer is yes, complete the next 3 questions. |  | No |  |  |  | Yes
|  |  |  | Level = 1 | Level = 2 | Level = 3 | Level = 4 | Level = 5
| 3.2 | How many data sources will use automated migration to a data warehouse requiring data transformation? If your answer is 1 or more, complete the next question. |  | 0 | 1 | 2 | 3 | 4+
| 3.3 | Will synchronization be required for each data transformation? If your answer is 1 source synchronization or more, complete the next question. |  | No synchronization | 1 source synchronized | 2 sources synchronized | 3 sources synchronized | 4+ sources synchronized
| 3.4 | How many iterations are planned for the project in which data synchronization will be required (legacy and new database)? |  | 0 iterations | 1 iterations | 2 iterations | 3 iterations | 4+ iterations
| 3.5 | What is the current overall state, quality, and reliability of the data residing in the existing system(s)? |  | Optimized Data is highly trusted, automated, and integrated across all systems | Well-Governed Data is accurate, well-documented, and governed | Baseline/Standardized Data is centralized, minor data errors, no automated data governance | Inconsistent Data is stored in disparate systems resulting in conflicting data | Unmanaged/Corrupted Data is fragmented and duplicated, with severe inaccuracies
| 3.6 | Select the scenario that best describes your anticipated solution. |  | COTS - SaaS: No Configuration Required | COTS - SaaS: Configuration Only | COTS - SaaS: with customization | COTS - SaaS: with customization and integration with existing database | Custom Development
| 3.7 | What is the degree of the state technical team's prior experience with the proposed solution or similar technology? |  | 4+ prior implementations | 3 prior implementations | 2 prior implementations | 1 prior implementation | 0 prior implementations
| 3.8 | Select the number of other systems with which the target processes will interact / interface. |  | Standalone | 1 | 2 | 3 | 4+
| 3.9 | What is the anticipated number of automated bi-directional data exchange interfaces? |  | 0 | 1 | 2 | 3 | 4+
| 3.10 | What is the anticipated number of manual bi-directional data exchange interfaces? |  | 0 | 1 | 2 | 3 | 4+
| 3.11 | What is the average daily volume of record transactions? |  | 1,000 or less | 1,001-5,000 | 5,001-10,000 | 10,001-25,000 | 25,001-50,000+
| 3.12 | What is the anticipated peak transaction volume (times daily volume)? |  | 2X+ | 5X | 10X | 25X | 50X+
| 3.13 | What is your anticipated weekly data record volume? |  | 1,000 or less | 1,001-10,000 | 10,001 - 1,000,000 | 1,000,001 - 10,000,000 | 10,000,001+
| 3.14 | What is your classification of data sensitivity and security? |  | Public | Internal | Confidential | Restricted/ Highly Confidential | Life & Safety
| 3.15 | What is your up-time availability/criticality/fault tolerance (per year)? (per Uptime Institute https://uptimeinstitute.com/) |  | Tier 1 - Basic 99.671% Non-Critical | Tier 2 - Redundant 99.741% Moderate Criticality | Tier 3 - Concurrent 99.982% Mission-Critical | Tier 4 - Fault Tolerant 99.995% Life & Safety | Tier 5 - Full fault Tolerant 99.999% Life, Safety & Environmental | Tier Definitions: https://www.coresite.com/blog/breaking-down-data-center-tiers-classifications
| 3.16 | Who is responsible for storing and managing the data? |  | None required | CDT cloud-managed hosting | Fully managed (commercial cloud-hosted or storage-as-a-service) | Vendor-managed (hybrid or shared cloud storage) | Self-managed (on-premise or self-hosted)
| 3.17 | Select the anticipated user base, including interfacing partners. |  | Within one department | Multi-department, one site | Agency-wide, multi-site | Multi-Agency, multi-site | Public-facing, statewide
| 3.18 | What is the number of primary external application development contractors/vendors engaged in the project? |  | 1 | 2 | 3 | 4 | 5+
| 3.19 | What is the number of ancillary external contractors/vendors engaged in the project? (IV&V, OCM, PM, BA, Testing, etc.) |  | 0 | 1 | 2 | 3 | 4+
| 3.20 | What is the total number of unique physical sites where this software application will be installed or deployed? |  | 1 | 2 | 3 | 4 | 5+
| 3.21 | What is the total number of individual user workstations, kiosks, or terminals geographically dispersed that will run the frontend application? |  | 100-300 | 301-500 | 501-600 | 601-900 | 901-1000+
|  | AVERAGE TOTAL | 0 | The higher your score, the more complex your project will be.

## Summary Score
SUMMARY
Knowledge Area | Average Score
Business | 0
Project Management/Governance | 0
Environment and Technology | 0
TOTAL AVERAGE SCORE | 0
Complexity Levels &
Scoring Ranges
| Low | 1.00-1.99
| Med | 2.00-2.99
| High | 3.00-4.24
| Very High | 4.25-5.00
If your score is 4 or greater in any given knowledge area, guidance should be sought from your PAO Manager.

## Heat Map and Spider Chart
HEAT MAP
Business | Project Management | Technical
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 |  | 0
0 |  | 0
0
0
0
0
0
0
0

## IV&V Determination
Independent Verification & Validation (IV&V) Questions
Based on IEEE Std 1012, the following questions have been extracted from the Project Complexity Assessment and scored to evaluate the Software Integrity Level (SIL) profile and determine if the project's risk profile warrants independent oversight.
Question # | Project Characteristics | IV&V? | Score Level for IV&V | PAO Evaluation Guidance
Business
1.1 | What is the estimated project cost? |  | 3-5
1.2 | What is the potential financial risk the project imposes on the State? |  | 3-5
1.4 | What is the primary impact on the State if this project is not completed? |  | 3-5
1.5 | What is the degree to which the project's outcome is visible to executives, external stakeholders, legislators, the Governor's Office, or the general public? |  | 3-5
1.6 | Specify the total number of users of the application. |  | 3-5 | Review answer to 3.16 to help determine the scale
1.7 | What is the degree to which organizational rules or regulations exist and may impact the project? |  | 3-5
1.8 | To what extent are documented business rules stable versus changing over a defined period (e.g., past 12 months)? |  | 3-5
1.1 | What is the degree to which existing business processes will be impacted by the project? |  | 3-5
1.11 | At what level have requirements been documented, validated, and traced? |  | 3-5 | Review questions 1.12, 1.13, and 3.5 in combination with this question
1.12 | What is the total number of agreed-upon functional requirements? |  | 3-5
1.13 | Of the total number of agreed-upon functional requirements, what percentage are mandatory versus optional? |  | 3-5
1.16 | What is the degree to which unanswered questions or differences of opinion exist about the project requirements? |  | 3-5
1.17 | What is the degree of influence on the project leadership asserted from external stakeholders, legislators, the Governor's Office, or the general public? |  | 3-5
Business AVG
Project Management/Governance
2.3 | Multiple/diverse stakeholder influence |  | 3-5
2.5 | How many dedicated state resources are required to complete this project? |  | 3-5 | Review Q # 3.17 for the number of vendors
2.6 | Project Sponsor limited/no experience/success on a project of similar size or complexity |  | 3-5 | Ask the department to provide documentation to support their answer. For high to very high complexity projects, the experience of the Project Director, Executive Director, Technical Lead, and the PMO Chief should also be considered.
2.7 | State PM limited/no experience/success on a project of similar size or complexity |  | 3-5 | Ask the department to provide documentation to support their answer. For high to very high complexity projects, the experience of the Project Director, Executive Director, Technical Lead, and the PMO Chief should also be considered.
2.8 | State project team limited/no experience/success on a project of similar size or complexity |  | 3-5 | Ask the department to provide documentation to support their answer. For high to very high complexity projects, the experience of the Project Director, Executive Director, Technical Lead, and the PMO Chief should also be considered.
2.1 | Are there constraints on the project schedule? |  | 3-5
Project Mgt & Governance AVG
Environmental & Technology
3.1 | Legacy system replacement? |  | 5=Yes
3.2 | Number of legacy data sources for migration |  | 3-5
3.6 | Select the scenario that best describes your anticipated solution. |  | 3-5 | Review questions 1.6, 1.9, 1.10, 1.11 & 1.12 in combination with this question.
3.7 | What is the degree of the state technical team's prior experience with the proposed solution or similar technology? |  | 3-5 | Ask department to provide evidence of "similar technology"
3.8 | Select the number of other systems with which the target processes will interact / interface. |  | 3-5 | Review in combination with 3.8 & 3.9
3.8 | What is the anticipated number of automated bi-directional data exchange interfaces? |  | 3-5 | Review in combination of 3.7 & 3.9
3.11 | What is the average daily volume of record transactions? |  | 3-5 | Review in combination with 3.11 & 3.14
3.12 | What is the anticipated peak transaction volume (times daily volume)? |  | 3-5 | Review in combination with 3.10 & 3.14
3.14 | What is your classification of data sensitivity and security? |  | 3-5
3.15 | What is your up-time availability/criticality/fault tolerance (per year)? |  | 3-5 | Review in combination with 3.10 & 3.11
3.16 | Who is responsible for storing and managing the data? |  | 3-5
3.17 | Select the anticipated user base, including interfacing partners. |  | 3-5
3.18 | What is the number of primary external application development contractors/vendors engaged in the project? |  | 3-5
Environmental & Technology AVG
TOTAL AVG
COMPLEXITY TRIGGERS ("Yes" to any of the below triggers, regardless of above complexity scoring, requires IV&V)
Question # | Project Characteristics | IV&V? | Score Level for IV&V | PAO Evaluation Guidance
1.1 | Estimated Project Cost |  | ≥$25M
1.3 | What is the anticipated funding source for the project? |  | ≥4
1.4 | Legislative, Financial, Audit, or Legal Impact |  | 2-5
3.8 | Number of external integrations |  | 2 or more
3.14 | Classification of data sensitivity & security |  | 3-5

## Values (hidden)
Chapters/Phase | Yes/No
Ideation Phase (Initial Assessment) | Yes
Chapter 1 | No
Chapter 2
Chapter 3
Chapter 4